## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
US-001 | TA: TA, I want to create my profile | As a TA, I want to create my profile so that I can apply once and reuse details. | Must | Sprint 1 | Profile saves with mandatory fields and is retrievable. | 5 | Status: Planned; Owner: YuhangFu | 2026-03-12 | 2026-03-22
US-002 | TA: TA, I want to upload CV metadata | As a TA, I want to upload CV metadata so that MO can review my capability. | Must | Sprint 1 | CV filename and upload time are persisted. | 3 | Status: Planned; Owner: Shuai Na | 2026-03-12 | 2026-03-22
US-003 | TA: TA, I want to view open jobs | As a TA, I want to view open jobs so that I can choose suitable roles. | Must | Sprint 1 | Open jobs list supports pagination and role/module display. | 5 | Status: Planned; Owner: YuhangFu | 2026-03-12 | 2026-03-22
US-004 | TA: TA, I want to submit an application | As a TA, I want to submit an application so that I can compete for a role. | Must | Sprint 1 | Application creates one idempotent record per applicationId. | 8 | Status: Planned; Owner: LeileiTao | 2026-03-12 | 2026-03-22
US-005 | TA: TA, I want to check application status | As a TA, I want to check application status so that I know progress. | Must | Sprint 1 | Status endpoint returns current state by applicantId. | 3 | Status: Planned; Owner: Ruiqi Guo | 2026-03-12 | 2026-03-22
US-006 | MO: MO, I want to post jobs | As an MO, I want to post jobs so that TAs can apply. | Must | Sprint 1 | Job post validates required fields and persists to jobs.jsonl. | 8 | Status: Planned; Owner: Jiajin He | 2026-03-12 | 2026-03-22
US-007 | MO: MO, I want to filter applicants by skills | As an MO, I want to filter applicants by skills so that shortlisting is faster. | Should | Sprint 2 | Filter returns only applicants with matching tags. | 5 | Status: Planned; Owner: Shuai Na | 2026-03-23 | 2026-04-12
US-008 | MO: MO, I want to update application status | As an MO, I want to update application status so that communication is clear. | Should | Sprint 2 | Status transitions follow valid state rules. | 5 | Status: Planned; Owner: Yi Zheng | 2026-03-23 | 2026-04-12
US-009 | Admin: As admin, I want workload summary | As admin, I want workload summary so that TA allocation stays fair. | Must | Sprint 1 | Workload endpoint returns per-TA counts and total. | 5 | Status: Planned; Owner: YuhangFu | 2026-03-12 | 2026-03-22
US-010 | Admin: As admin, I want over-allocation alerts | As admin, I want over-allocation alerts so that risk is visible. | Could | Sprint 3 | Any TA over threshold is highlighted. | 3 | Status: Planned; Owner: Ruiqi Guo | 2026-04-13 | 2026-05-03
US-011 | System: As system, I need JSONL storage | As system, I need JSONL storage so that DB is not required. | Must | Sprint 1 | All entities persist into text files only. | 8 | Status: Planned; Owner: YuhangFu | 2026-03-12 | 2026-03-22
US-012 | System: As system, I need append-only writes | As system, I need append-only writes so that crashes do not corrupt old data. | Must | Sprint 1 | Write path appends and keeps previous lines intact. | 5 | Status: Planned; Owner: LeileiTao | 2026-03-12 | 2026-03-22
US-013 | System: As system, I need atomic compaction | As system, I need atomic compaction so that large files remain manageable. | Should | Sprint 2 | Compaction writes temp file then atomic replace. | 8 | Status: Planned; Owner: Jiajin He | 2026-03-23 | 2026-04-12
US-014 | System: As system, I need lightweight indexes | As system, I need lightweight indexes so that startup and query remain efficient. | Should | Sprint 2 | id/status indexes built without loading full objects. | 5 | Status: Planned; Owner: YuhangFu | 2026-03-23 | 2026-04-12
US-015 | User: user, I want mobile-friendly pages | As a user, I want mobile-friendly pages so that app works on phones. | Must | Sprint 1 | Core pages pass responsive breakpoint checks. | 5 | Status: Planned; Owner: Yi Zheng | 2026-03-12 | 2026-03-22
US-016 | User: user, I want a high-recognition UI style | As a user, I want a high-recognition UI style so that product feels polished. | Should | Sprint 1 | Glass-card visual system applied consistently. | 3 | Status: Planned; Owner: Shuai Na | 2026-03-12 | 2026-03-22
US-017 | QA: As QA, I want unit tests on service and repository | As QA, I want unit tests on service and repository so that regressions are caught. | Must | Sprint 1 | Critical logic has deterministic tests. | 5 | Status: Planned; Owner: YuhangFu | 2026-03-12 | 2026-03-22
US-018 | QA: As QA, I want integration tests for workflow | As QA, I want integration tests for workflow so that end-to-end behavior is verified. | Should | Sprint 2 | Post job -> apply -> query -> workload passes. | 8 | Status: Planned; Owner: LeileiTao | 2026-03-23 | 2026-04-12
US-019 | Security: As system, I want basic input validation | As system, I want basic input validation so that malformed requests are rejected. | Must | Sprint 1 | Invalid parameters return explicit 400 errors. | 3 | Status: Planned; Owner: Jiajin He | 2026-03-12 | 2026-03-22
US-020 | DevOps: As team, I want branch/PR conventions | As team, I want branch/PR conventions so that contribution evidence is clear. | Must | Sprint 1 | README documents branch workflow and PR policy. | 2 | Status: Done; Owner: YuhangFu | 2026-03-12 | 2026-03-22