## Backlog
Story ID | Role | User Story | Acceptance Criteria | Priority(MoSCoW) | Estimate(Fibonacci) | Sprint | Status | Owner
US-001 | TA | As a TA, I want to create my profile so that I can apply once and reuse details. | Profile saves with mandatory fields and is retrievable. | Must | 5 | Sprint 1 | Planned | YuhangFu
US-002 | TA | As a TA, I want to upload CV metadata so that MO can review my capability. | CV filename and upload time are persisted. | Must | 3 | Sprint 1 | Planned | ShuaiNa
US-003 | TA | As a TA, I want to view open jobs so that I can choose suitable roles. | Open jobs list supports pagination and role/module display. | Must | 5 | Sprint 1 | Planned | YuhangFu
US-004 | TA | As a TA, I want to submit an application so that I can compete for a role. | Application creates one idempotent record per applicationId. | Must | 8 | Sprint 1 | Planned | Member-3
US-005 | TA | As a TA, I want to check application status so that I know progress. | Status endpoint returns current state by applicantId. | Must | 3 | Sprint 1 | Planned | Member-4
US-006 | MO | As an MO, I want to post jobs so that TAs can apply. | Job post validates required fields and persists to jobs.jsonl. | Must | 8 | Sprint 1 | Planned | Member-5
US-007 | MO | As an MO, I want to filter applicants by skills so that shortlisting is faster. | Filter returns only applicants with matching tags. | Should | 5 | Sprint 2 | Planned | ShuaiNa
US-008 | MO | As an MO, I want to update application status so that communication is clear. | Status transitions follow valid state rules. | Should | 5 | Sprint 2 | Planned | Member-6
US-009 | Admin | As admin, I want workload summary so that TA allocation stays fair. | Workload endpoint returns per-TA counts and total. | Must | 5 | Sprint 1 | Planned | YuhangFu
US-010 | Admin | As admin, I want over-allocation alerts so that risk is visible. | Any TA over threshold is highlighted. | Could | 3 | Sprint 3 | Planned | Member-4
US-011 | System | As system, I need JSONL storage so that DB is not required. | All entities persist into text files only. | Must | 8 | Sprint 1 | Planned | YuhangFu
US-012 | System | As system, I need append-only writes so that crashes do not corrupt old data. | Write path appends and keeps previous lines intact. | Must | 5 | Sprint 1 | Planned | Member-3
US-013 | System | As system, I need atomic compaction so that large files remain manageable. | Compaction writes temp file then atomic replace. | Should | 8 | Sprint 2 | Planned | Member-5
US-014 | System | As system, I need lightweight indexes so that startup and query remain efficient. | id/status indexes built without loading full objects. | Should | 5 | Sprint 2 | Planned | YuhangFu
US-015 | User | As a user, I want mobile-friendly pages so that app works on phones. | Core pages pass responsive breakpoint checks. | Must | 5 | Sprint 1 | Planned | Member-6
US-016 | User | As a user, I want a high-recognition UI style so that product feels polished. | Glass-card visual system applied consistently. | Should | 3 | Sprint 1 | Planned | ShuaiNa
US-017 | QA | As QA, I want unit tests on service and repository so that regressions are caught. | Critical logic has deterministic tests. | Must | 5 | Sprint 1 | Planned | YuhangFu
US-018 | QA | As QA, I want integration tests for workflow so that end-to-end behavior is verified. | Post job -> apply -> query -> workload passes. | Should | 8 | Sprint 2 | Planned | Member-3
US-019 | Security | As system, I want basic input validation so that malformed requests are rejected. | Invalid parameters return explicit 400 errors. | Must | 3 | Sprint 1 | Planned | Member-5
US-020 | DevOps | As team, I want branch/PR conventions so that contribution evidence is clear. | README documents branch workflow and PR policy. | Must | 2 | Sprint 1 | Done | YuhangFu